# BTP Project Timeline: Immersive VR CAD Interface

Updated Aug 18, 2026 — Phase 1 revised to reflect current work.

## Project Timeline & Estimated Dates

| Phase | Estimated Dates | Category | Specific Deliverables | Status |
| --- | --- | --- | --- | --- |
| Phase 1 | Aug 10 – Aug 19 | Architecture | Migrate legacy VR architecture to OpenXR for MQ2 support: strip SteamVR, install OpenXR + Meta XR SDK + XRI, rebuild camera rig as XR Origin. | In Progress |
| Phase 1 | Aug 19 – Aug 28 | Programming | Refactor broken C# scripts to the new Unity Input System; rewire interactable objects (grab/throw) to XRI's XRGrabInteractable. | Pending |
| Phase 1 | Aug 28 – Sept 10 | Testing & Debugging | Build and deploy to Meta Quest 2 (Android/IL2CPP); validate XR Origin tracking, controller input, and grab interactions on-device; resolve build/runtime errors. | Pending |
| Phase 1 | Sept 10 – Sept 19 | Buffer / Contingency | Reserved slack to absorb migration overrun; close out any unfinished input/interactable rewiring; merge task-1 branch into main before Phase 2 begins. | Pending |
| Phase 2 | Sept 20 – Sept 26 | Mechanics | Implement precise face, vertex, and edge selection tools. | Upcoming |
| Phase 2 | Sept 26 – Sept 30 | Mechanics | Establish robust coordinate/reference systems for geometry. | Upcoming |
| Phase 2 | Oct 1 – Oct 6 | Interaction | Integrate bare-hand gestures alongside MQ2 controllers. | Upcoming |
| Phase 2 | Oct 6 – Oct 12 | Features | Program initial operations: Holes, Chamfering, and Bevelling. | Upcoming |
| Phase 2 | Oct 12 – Oct 15 | UX/UI | Enable users to build and extrude directly from any selected face. | Upcoming |
| Phase 3 | Oct 15 – Nov 5 | Features | Program advanced operations: Fillets and Revolve. | Upcoming |
| Phase 3 | Nov 5 – Nov 20 | Polish | Debug and finalize Chamfering, Bevelling, and Hole tools. | Upcoming |
| Phase 3 | Nov 20 – Nov 28 | Constraints | Enforce strict mechanical constraints (strictly no freehand sketching). | Upcoming |
| Phase 3 | Nov 28 – Dec 1 | Finalization | Final bug fixes, project packaging, and documentation. | Upcoming |